## Slide 1
Brainstorming (8 hours)
Market Research (16 hours)
Defining Core Features & MVP Scope (24 hours)
Writing Detailed Project Specifications (32 hours)
Start designing
Wireframing all screens (40 hours)
Internal Review & Revisions (16 hours of rework/delay)
Creating High-Fidelity Mockups & Prototypes (56 hours)
Creating Asset Library (icons, fonts, etc.) (8 hours)
Start development
Project Setup & Scaffolding (16 hours)
Building UI Components from Mockups (80 hours)
Implementing State Management (80 hours)
API Integration & Backend Communication (40 hours)
Start testing
Preparing App Store Listings (8 hours)
Building & Signing Release Binaries (8 hours)
Submitting to App Stores (4 hours)
App Store Review (up to 1 week of non-work delay)
Respond to Reviewer Feedback / Rejections (10 hours)
Release to Production (2 hours)
Development:
Design:
Planning:
Deployment
Writing Test Cases (16 hours)
Manual Functional Testing (32 hours)
Bug Reporting & Triage (8 hours)
Bug Fixing (24 hours of development time)
Handoff for Deployment
Testing
Optimization:
Have basic UX/UI style guide done, and component library chosen
Have navigation shell set. (80 hours/2 weeks)
---
Plan features and have them written down
Design mockups based on these features (80 hours/2 weeks)
Testing throughout, so bugs are fixed right away (16 hours)
---
Final regression testing
App store listing
Submit to app stores (1 week)
---
App building VSM
Jonathan Davis Module 5 6/29/2025
This is a VSM I built up, around the application that I am currently building through vscode and react-native. All times are best estimations I can give at the moment.
By designing features and testing them as I go, I can cut out a lot of time. This is because I won’t have to wait to get to a testing phase to debug and will have mockups made as features change. Also, by having simple mockups made, they can be easily manipulated as I design the app’s backend and API integration. As the sole builder, designer and QA person on the project, I can save around 100-200 hours depending on complexity of features, designing, severity of bugs. Overall, I save a lot of time by doing certain things as I go, versus in strict step by steps.